## Features
S.No	Feature Required	Deadline	Started Working On	Completed On	Comments
1	Send email during assignment of task.	19th Aug	19th Aug	19th Aug	We are using slack feature which notifies the user if the message goes unread
2	Send email after accepting and rejecting any task.	19th Aug	19th Aug	19th Aug	We are using slack feature which notifies the user if the message goes unread
3	Whenever user is assigned any task. Taskbot should notify assignee through a proper message.	19th Aug	19th Aug	19th Aug	User's taskbot notifies in case of any task assignment.
4	User should be able to supply date while task creation.	20th Aug	20th Aug
5	Set reminder for a task.	21St Aug
6	Change the response and make taskbot more interactive.	24th Aug
7	Add search function to find tasks containing keywords	25th Aug	20th Aug	20th Aug	User can search tasks based on keywords

## Issues
S.No	Issues	Deadline	Started Working On	Completed On
1	Default date and time are system specific and not user specific.	19th Aug	19th Aug	20th Aug
2	While creating subtask, use the last 'for' in the description.	20th Aug	20th Aug	20th Aug